## HighLevelPlan
ProjectName | [17 empty] | The Team
StartDate | 2020-04-21
EndDate | 2020-07-07
Duration(Days) | 77
Milestones | Duration | Start | End | 2020-04-21 | 2020-04-28 | 2020-05-05 | 2020-05-12 | 2020-05-19 | 2020-05-26 | 2020-06-02 | 2020-06-09 | 2020-06-16 | 2020-06-23 | 2020-06-30 | 2020-07-07 | 2020-07-14 | 2020-07-21
Team | 7 | 2020-04-21 | 2020-04-28 | X | X
High Level Plan | 7 | 2020-04-21 | 2020-04-28 | X | X
Project Plan | 7 | 2020-04-28 | 2020-05-05 |  | X | X
Conceptual Model | 14 | 2020-04-28 | 2020-05-12 |  | X | X | X
Data Analysis | 28 | 2020-04-28 | 2020-05-26 |  | X | X | X | X | X
Simulation Program | 28 | 2020-05-05 | 2020-06-02 |  |  | X | X | X | X | X
Validation | 40 | 2020-05-07 | 2020-06-16 |  |  |  | X | X | X | X | X | X
Experiments | 28 | 2020-06-02 | 2020-06-30 | [6 empty] | X | X | X | X | X
Final Report | 60 | 2020-05-08 | 2020-07-07 |  |  |  | X | X | X | X | X | X | X | X | X

## Copy of HighLevelPlan
ProjectName | [17 empty] | The Team
StartDate | 2020-04-21
EndDate | 2020-07-07
Duration(Days) | 77
Milestones | Duration | Start | End | 2020-04-21 | 2020-04-28 | 2020-05-05 | 2020-05-12 | 2020-05-19 | 2020-05-26 | 2020-06-02 | 2020-06-09 | 2020-06-16 | 2020-06-23 | 2020-06-30 | 2020-07-07 | 2020-07-14 | 2020-07-21
Team | 7 | 2020-04-21 | 2020-04-28 | X | X
High Level Plan | 7 | 2020-04-21 | 2020-04-28 | X | X
Project Plan | 7 | 2020-04-28 | 2020-05-05 |  | X | X
Conceptual Model | 14 | 2020-04-28 | 2020-05-12 |  | X | X | X
Data Analysis | 28 | 2020-04-28 | 2020-05-26 |  | X | X | X | X | X
Simulation Program | 28 | 2020-05-05 | 2020-06-02 |  |  | X | X | X | X | X
Validation | 40 | 2020-05-07 | 2020-06-16 |  |  |  | X | X | X | X | X | X
Experiments | 28 | 2020-06-02 | 2020-06-30 | [6 empty] | X | X | X | X | X
Final Report | 60 | 2020-05-08 | 2020-07-07 |  |  |  | X | X | X | X | X | X | X | X | X

## KANBAN
Bucket | IN PROGRESS | PRESENTATION PREPERATION | REWORK | INTERNAL ASSESSMENT | DONE | Home
MS1_1
MS1_2
MS1_3

## Members
Home
Name | Project Role
Arnab Das

## Team
| Milestone Home Work | e-mail-list for the team, Dropbox or other team & project collaboration tool print and sign team goal detailed list of personal and general performance and quality criteria naming a team member who will be responsible for holding the team to these standards Expressive photographs of current traffic situation What is spacial there What data will you need for the simulation model Which four (!) experiments would you like to conduct | [7 empty] | Home
TaskID | Task Name | Pre - Requisite | Goal | Exit Criteria | Lesson Learned | Reason For Delay | Initial Estimation | Actual Time Taken | Time BreakDown | Owner
MS1_1 | Role Assigment | 1) Understanding of individual Role | Happy Team with all assigned roles Clear Understanding of responsibility | 1) Roles Distributed 2) Team Goal Decided and signed. 3) Team Standard decided - Owner identificaton 4) Performace Measuring Criteria selected 5) Quality Assurance criteria Selected |  |  | 12
MS1_2 | MS1: Documentation
MS1_3 | MS1: Homework

## Kosten
| Tolerance | 2% | milestone | plan | actual | sum plan | sim actual | Planned Costs | Home
|  |  | Team | 55 | 55 | 55 |  | Actual Costs
10.64% | 25 | 7% | Plan | 38.15 |  | 93.15 |  | Planned Cumulative Costs
17.02% | 40 | 12% | Concept | 65.4 |  | 158.55 |  | Actual Cumulative Costs
12.77% | 30 | 20% | Data | 109 |  | 267.55
29.79% | 70 | 20% | Model | 109 |  | 376.55
8.511% | 20 | 18% | Validation | 98.1 |  | 474.65
12.77% | 30 | 16% | Experiments | 87.2 |  | 561.85
8.511% | 20 | 7% | Report | 38.15 |  | 600
235
|  |  | Total | 600
|  |  | Remaining | 0
| 545 | 100%

## Milestone2
Milestone 3: Conceptual Plan
ID | Description | Dependency | Assignee | Effort (%) | Hours | Remaining | 0%
1 | Draw the Petri Net |  | Chandan | 40% | 26.16 | Total hours | 65.4
1.1 | Petri net concept |  | Chandan |  | 0
1.1.1 | Define the events and states |  | Chandan |  | 0
1.1.2 | Define the assumptions with justification |  | Chandan |  | 0
1.1.3 | Define the quantities to be measured |  | Chandan |  | 0
1.1.4 | Define the quantities to be used as simulation results |  | Chandan |  | 0
2 | Review Petri net |  | Everyone | 10% | 6.54
3 | Draw Petri net diagram electronically |  | Chandan | 10% | 6.54
4 | Go through the milestone documentation and think about each of the questions |  | Everyone | 10% | 6.54
5 | Precisely define the experiments that will be performed in terms of changes in the Petri net | 3 | Arnab / Vinay | 10% | 6.54
6 | Prepare presentation | 1, 2, 3, 4, 5 | Chandan | 10% | 6.54
7 | Milestone-related discussions |  | Everyone | 10% | 6.54

## Milestone3
Milestone 3: Conceptual Plan
ID | Description | Dependency | Assignee | Effort (%) | Hours | Remaining | 0%
1 | Draw the Petri Net |  | Chandan | 40% | 26.16 | Total hours | 65.4
1.1 | Petri net concept |  | Chandan |  | 0
1.1.1 | Define the events and states |  | Chandan |  | 0
1.1.2 | Define the assumptions with justification |  | Chandan |  | 0
1.1.3 | Define the quantities to be measured |  | Chandan |  | 0
1.1.4 | Define the quantities to be used as simulation results |  | Chandan |  | 0
2 | Review Petri net |  | Everyone | 10% | 6.54
3 | Draw Petri net diagram electronically |  | Chandan | 10% | 6.54
4 | Go through the milestone documentation and think about each of the questions |  | Everyone | 10% | 6.54
5 | Precisely define the experiments that will be performed in terms of changes in the Petri net | 3 | Arnab / Vinay | 10% | 6.54
6 | Prepare presentation | 1, 2, 3, 4, 5 | Chandan | 10% | 6.54
7 | Milestone-related discussions |  | Everyone | 10% | 6.54

## Milestone4
Milestone 4 : Data analysis
ID | Description | Dependency | Assignee | Effort (%) | Hours | Remaining | 0% | spent | time left
1 | Estimate the underlying distributions |  |  | 45% | 49.05 | Total hours | 109 | 2 | 107
1.1 | Analyze the data from the city of Magdeburg |  |  |  | 0
1.1.1 | separate the data according to the given data for various locations of the node |  |  |  | 0
1.1.2 | separate the data based on type of vehicle(pedestrians/bicyclists, cars, bus, tram) and calculate the probability of the directions taken |  |  |  | 0
1.1.3 | identify the ssuitable inter arrival time(exp) distribution for each vehicle from each location of the node |  |  |  | 0
1.1.4 | detect autocorrelation plot the histogram and make guess of type of distribution for the count of vehicles(entry and exit) for each location specified |  |  |  | 0
1.1.5 | generate the q-q plot and tune the parameters(mean, sd) and perform chi square test and get the reliable distribution function |  |  |  | 0
1.2 | Analyze last year data as well as api data(same steps as above) |  |  | 35% | 38.15
1.2.1 | Analyze data collected by group |  |  |  | 0
2 | prepare presentation |  | vinay | 13% | 14.17
3 | Milestone discussion |  | everyone | 7% | 7.63

## Milestone6
Milestone 6: Validation and quality control
ID | Description | Dependency | Assignee | Effort (%) | Hours | Remaining | 20%
1 | Output analysis |  |  | 40% | 26.16 | Total hours | 65.4
1.1 | Calculate statistics on the variables of the model |  | Lauro |  | 0
1.1.1 | Confidence intervals |  |  |  | 0
2 | Compare simulation output data with real data |  |  | 10% | 6.54
2.1 | Update the model where it is not performing similar to the real data collected |  | Anjan | 10% | 6.54
3 | Prepare presentation | 2020-02-01 | Anjan | 10% | 6.54
4 | Milestone-related discussions |  | Everyone | 10% | 6.54

## Milestone7
Milestone 7: Experiments
ID | Description | Dependency | Assignee | Effort (%) | Hours | Remaining | 0%
1 | Create dedicated models for each experiment |  | Arnab | 30% | 26.16 | Total hours | 87.2
1.1 | Description and justification of experiments performed |  | Lauro |  | 0
1.2 | Find variables of interest |  | Everyone
2 | Perform the experiments on the model | 1 | Anjan | 40% | 34.88
2.1 | Output analysis for each of the experiments |  | Anjan |  | 0
2.2 | Analyze each experiment output and compare to vanilla data |  | Arnab |  | 0
2.3 | Draw conclusion from the experiment result - whether it helped or not to achieve the goal |  | Everyone |  | 0
2.4 | Statement of accuracy for interesting system variables |  | Arnab
3 | Identify Final recommendation for the customer | 1,2 | Everyone | 10% | 8.72
4 | Prepare presentation | 1,2,3 | Arnab | 8% | 6.976
5 | Milestone-related discussions |  | Everyone | 10% | 8.72
6 | Tolerance |  |  | 2% | 1.744

## Milestone8
Milestone 8: Final report
ID | Description | Dependency | Assignee | Effort (%) | Hours | Remaining | 0%
1 | Create the final report document. |  | Lauro | 3% | 1.1445 | Total hours | 38.15
2 | Overview Section: Provide an overview of each milestone, the problems encountered, and the solutions for each of the problems. |  | Lauro | 7% | 2.6705
3 | Conceptual Model Section: Explain the conceptual model by focusing on the assumptions made by the team. |  | Lauro | 7% | 2.6705
4 | Data Analysis Section: Explain the results of the data analysis and the distributions used to model the system. |  | Lauro | 10% | 3.815
5 | Validation Section: Explain the limitations of the model, as well as the modifications made in order to make it more realistic. |  | Lauro | 10% | 3.815
6 | Recommendations Section: Explain the relevant experiments, their results and their feasibility. |  | Lauro | 10% | 3.815
7 | Cost Overview Section: Provide an overview of the cost spent per milestone, as well as comments on how the planned costs were adjusted to deal with unforeseen challenges. |  | Lauro | 5% | 1.9075
8 | Team Section: Provide an overview of the team as a whole during the project, how we have worked together, whether there were any challenges. |  | Lauro | 10% | 3.815
9 | Team Section: For each of the members, provide an overview of the project performance, as well as personal comments regarding the course. |  | Lauro | 10% | 3.815
10 | Format the final report. |  | Lauro | 5% | 1.9075
11 | Read and review the final report. | All previous tasks | Everyone | 15% | 5.7225
12 | Implement changes from the review of the final report. | 11 | Lauro | 8% | 3.052