## HighLevelPlan
\
ProjectName
| StartDate | 2020-04-21
| EndDate | 2020-07-07
\\ | Duration(Days) | 77
| Milestones | Duration | Start | End | 2020-04-21 | 2020-04-28 | 2020-05-05 | 2020-05-12 | 2020-05-19 | 2020-05-26 | 2020-06-02 | 2020-06-09 | 2020-06-16 | 2020-06-23 | 2020-06-30 | 2020-07-07 | 2020-07-14 | 2020-07-21
| Team | 7 | 2020-04-21 | 2020-04-28 | X | X
| High Level Plan | 7 | 2020-04-21 | 2020-04-28 | X | X
| Project Plan | 7 | 2020-04-28 | 2020-05-05 |  | X | X
| Conceptual Model | 14 | 2020-04-28 | 2020-05-12 |  | X | X | X
| Data Analysis | 28 | 2020-04-28 | 2020-05-26 |  | X | X | X | X | X
| Simulation Program | 28 | 2020-05-05 | 2020-06-02 |  |  | X | X | X | X | X
| Validation | 33 | 2020-05-14 | 2020-06-16 |  |  |  |  | X | X | X | X | X
| Experiments | 28 | 2020-06-02 | 2020-06-30 | [6 empty] | X | X | X | X | X
| Final Report | 50 | 2020-05-18 | 2020-07-07 |  |  |  |  | X | X | X | X | X | X | X | X

## Costs
Percentage effort | Milestone | Plan | Actual | Sum plan | Sum actual
| Team | 55 | 55.4 | 55 | 55.4
7% | Plan | 36.05 | 33.5 | 91.05 | 88.9
12% | Concept | 61.8 | 53.75 | 152.85 | 142.65
20% | Data | 103 | 99.7 | 255.85 | 242.35
20% | Model | 103 | 84.9 | 358.85 | 327.25
18% | Validation | 92.7 | 111.8 | 451.55 | 439.05
16% | Experiments | 82.4 | 111.05 | 533.95 | 550.1
7% | Report | 36.05 | 46.45 | 570 | 596.55
| Total | 570
| Remaining | 30
100%
515

## Milestone3
Milestone 3: Conceptual Plan
ID | Description | Assignee | Supporters | Effort (%) | Hours | Remaining | 0%
1 | Draw the Petri Net | Chandan | Lauro Anjan Kavya | 40% | 24.72 | Total hours | 61.8
1.1 | Petri net concept |  |  |  | 0
1.1.1 | Define the events and states |  |  |  | 0
1.1.2 | Define the assumptions with justification |  |  |  | 0
1.1.3 | Define the quantities to be measured |  |  |  | 0
1.1.4 | Define the quantities to be used as simulation results |  |  |  | 0
2 | Draw Petri net diagram electronically |  |  | 10% | 6.18
3 | Review Petri Net | Everyone |  | 10% | 6.18
4 | Go through the milestone documentation and think about each of the questions | Everyone |  | 10% | 6.18
5 | Precisely define the experiments that will be performed in terms of changes in the Petri net | Arnab | Vinay | 10% | 6.18
6 | Prepare presentation | Chandan |  | 10% | 6.18
7 | Milestone-related discussions | Everyone |  | 10% | 6.18

## Milestone4
Milestone 4 : Data analysis
ID | Description | Assignee | Supporters | Effort (%) | Hours | Dependencies | Planned starting date | Planned end date | Remaining | 0%
1 | Estimate the underlying distributions | Vinay | Lauro Chandan Arnab |  |  | Data from MD and previous year | 27.04.2020 | 20.05.2020 | Total hours | 103
1.1 | Analyze the data from the city of Magdeburg |  |  | 25% | 25.75 | Data from MD
1.1.1 | Separate the data according to the given data for various locations of the node |  |  |  |  | Data from MD | 27.04.2020 | 29.04.2020
1.1.2 | Calculate the probability of the directions taken by each entity in the model |  |  |  |  | 1.1.1 | 11.05.2020 | 15.05.2020
1.2 | Analyze the data from the previous year |  |  | 28% | 28.84 | Data from previous year
1.2.1 | Identify the suitable inter arrival time(exp) distribution for each vehicle from each location of the node |  |  |  |  | Data from previous year | 06.05.2020 | 13.05.2020
1.2.2 | Detect autocorrelation, plot the histogram and make guess of type of distribution for the count of vehicles (entry and exit) for each location specified |  |  |  |  | 1.2.1 | 13.05.2020 | 17.05.2020
1.2.3 | Generate the q-q plot and tune the parameters(mean, sd) and perform chi square test and get the reliable distribution function |  |  |  |  | 1.2.1 | 15.05.2020 | 19.05.2020
2 | Analyze Tomtom api data (same steps as above) | Lauro | Anjan | 5% | 5.15 | - | 14.05.2020 | 15.05.2020
3 | Collect data at the node | ?? |  | 10% | 10.3 | - | ? | ?
3.1 | Analyze data collected by group | Kavya |  | 5% | 5.15 | 3 | ? | ?
5 | Prepare presentation | Vinay |  | 10% | 10.3 | 1, 2, 3 | 18.05.2020 | 22.05.2020
6 | Prepare milestone documentation |  |  | 10% | 10.3 | 1, 2, 3 | 18.05.2020 | 22.05.2020
7 | Milestone discussion | Everyone |  | 7% | 7.21 | 5, 6 | 23.05.2020 | 25.05.2020

## Milestone5
Milestone 5 : Simulation Program
ID | Description | Assignee | Supporters | Effort (%) | Hours | Dependencies | Planned starting date | Planned end date | Remaining | 0%
1 | Learning about the Road Traffic library | Everyone |  | 15% | 15.45 | - | 10.05.2020 | 16.05.2020 | Total hours | 103
2 | Build simulation model | Kavya | Arnab Vinay Lauro | 45% | 46.35
2.1 | Draw the roads and traffic signals in the network model |  |  |  |  | 1 | 11.05.2020 | 15.05.2020
2.2 | Implement vechicle generation and traffic flow with dummy distributions |  |  |  |  | 2.1 | 16.05.2020 | 19.05.2020
2.3 | Implement the correct distributions from the data analysis |  |  |  |  | 2.2, M4-1.2 | 19.05.2020 | 21.05.2020
2.4 | Define relevant functions, transitions, events, variables and constants relevant to the system specifications and input data |  |  |  |  | 2.2 | 19.05.2020 | 21.05.2020
2.5 | Code simulation program to represent the behavior in the conceptual model |  |  |  |  | 2.4 | 19.05.2020 | 25.05.2020
3 | Run the model and analyse its behaviour | Anjan |  | 20% | 20.6 | 2 | 25.05.2020 | 28.05.2020
4 | Buffer to further verify the model with conceptual design and do neccessary changes | Chandan |  |  |  | 2, M3 | 25.05.2020 | 28.05.2020
5 | Prepare presentation | Kavya |  | 10% | 10.3 | 3 | 28.05.2020 | 31.05.2020
6 | Prepare documentation |  |  |  |  | 3 | 28.05.2020 | 31.05.2020
7 | Milestone-related discussions | Everyone |  | 10% | 10.3 | 2020-05-04 | 26.05.2020 | 01.06.2020

## Milestone6
Milestone 6: Validation and quality control
ID | Description | Assignee | Supporters | Effort (%) | Hours | Dependencies | Planned starting date | Planned end date | Remaining | 0%
1 | Review implementation of roads and traffic lights. | Anjan | Kavya Arnab | 5% | 4.635 | M5-2.1 | 15.05.2020 | 17.05.2020 | Total hours | 92.7
2 | Review implementation of vechicle generation and traffic flow with dummy distributions. |  |  | 5% | 4.635 | M5-2.2 | 19.05.2020 | 21.05.2020
3 | Review implementation of the correct distributions from the data analysis. |  |  | 5% | 4.635 | M5-2.3 | 21.05.2020 | 23.05.2020
4 | Review the code of the simulation program. |  |  | 5% | 4.635 | M5-2.5 | 25.05.2020 | 27.05.2020
5 | Update the model where it shows inconsistencies or is not performing according to what is expected from the system in terms of "normal behavior" | Kavya | Lauro | 15% | 13.905 | M5-3, M5-4 | 28.05.2020 | 02.06.2020
6 | Output analysis: calculate mean, standard deviation, CI, and sensitivity analysis for the following variables | Lauro | Chandan Vinay |  |  | 5
6.1 | Average cars between source and sink |  |  | 8.75% | 8.1113 | 5 | 02.06.2020 | 08.06.2020
6.2 | Queue length for each of the lanes |  |  | 8.75% | 8.1113 | 5 | 02.06.2020 | 08.06.2020
6.3 | Average time cars take to travel between source and sink |  |  | 8.75% | 8.1113 | 5 | 05.06.2020 | 11.06.2020
6.4 | Amount of cars passing through a transition |  |  | 8.75% | 8.1113 | 5 | 05.06.2020 | 11.06.2020
7 | Prepare presentation | Anjan |  | 10% | 9.27 | 1 - 6 | 11.06.2020 | 14.06.2020
8 | Prepare documentation | Anjan |  | 10% | 9.27 | 1 - 6 | 11.06.2020 | 14.06.2020
9 | Milestone-related discussions | Everyone |  | 10% | 9.27 | - | 08.06.2020 | 15.06.2020

## Milestone7
Milestone 7: Experiments
ID | Description | Assignee | Supporters | Effort (%) | Hours | Dependencies | Planned starting date | Planned end date | Remaining | 0%
1 | Create dedicated models for each experiment: describe and justify the experiment | Arnab | Anjan Chandan Lauro |  |  | M5-3 |  |  | Total hours | 82.4
1.1 | Experiment 1: Vary traffic light duration |  |  | 5% | 4.12 | M5-3 | 02.06.2020 | 08.06.2020
1.2 | Experiment 2: Open traffic lights for each direction in different phases. |  |  | 5% | 4.12 | M5-3 | 02.06.2020 | 08.06.2020
1.3 | Experiment 3: Include a free lane to turn right for cars from Leipziger str. to Erich-Weinert str. |  |  | 5% | 4.12 | M5-3 | 02.06.2020 | 08.06.2020
1.4 | Experiment 4: Allow car traffic on the blocked tram line in Leipziger Str. |  |  | 5% | 4.12 | M5-3 | 02.06.2020 | 08.06.2020
1.5 | Experiment 5: Overload the system and check the behaviour of the traffic |  |  | 5% | 4.12 | M5-3 | 02.06.2020 | 08.06.2020
1.6 | Experiment 6: Bridge for cars going straight in Erich-Weinert-Straße / Am Fuchsberg |  |  | 5% | 4.12 | M5-3 | 02.06.2020 | 08.06.2020
2 | Conduct experiment 1 | Anjan | Arnab | 6% | 4.944 | 1, M6-5 | 09.06.2020 | 15.06.2020
2.1 | Perform the experiments on the model |  |  |  |  | 1, M6-5
2.2 | Output analysis as per M6-6 |  |  |  |  | 1, M6-5
3 | Conduct experiment 2 | Arnab | Chandan | 6% | 4.944 | 1, M6-5 | 09.06.2020 | 15.06.2020
3.1 | Perform the experiments on the model |  |  |  |  | 1, M6-5
3.2 | Output analysis as per M6-6 |  |  |  |  | 1, M6-5
4 | Conduct experiment 3 | Chandan | Kavya | 6% | 4.944 | 1, M6-5 | 09.06.2020 | 15.06.2020
4.1 | Perform the experiments on the model |  |  |  |  | 1, M6-5
4.2 | Output analysis as per M6-6 |  |  |  |  | 1, M6-5
5 | Conduct experiment 4 | Kavya | Lauro | 6% | 4.944 | 1, M6-5 | 09.06.2020 | 15.06.2020
5.1 | Perform the experiments on the model |  |  |  |  | 1, M6-5
5.2 | Output analysis as per M6-6 |  |  |  |  | 1, M6-5
6 | Conduct experiment 5 | Lauro | Vinay | 6% | 4.944 | 1, M6-5 | 09.06.2020 | 15.06.2020
6.1 | Perform the experiments on the model |  |  |  |  | 1, M6-5
6.2 | Output analysis as per M6-6 |  |  |  |  | 1, M6-5
7 | Conduct experiment 6 | Viany | Arnab | 6% | 4.944 | 1, M6-5 | 09.06.2020 | 15.06.2020
7.1 | Perform the experiments on the model |  |  |  |  | 1, M6-5
7.2 | Output analysis as per M6-6 |  |  |  |  | 1, M6-5
8 | Draw conclusion from the experiment result - whether it helped or not to achieve the goal | Arnab | Everyone | 5% | 4.12 | 2020-07-01 | 16.06.2020 | 20.06.2020
9 | Statement of accuracy for interesting system variables | Arnab | Anjan | 5% | 4.12 | 2020-07-01 | 16.06.20 | 22.06.2020
10 | Identify Final recommendation for the customer | Everyone |  | 5% | 4.12 | 8,9 | 22.06.2020 | 25.06.2020
11 | Prepare presentation | Arnab |  | 5% | 4.12 | 10 | 25.06.2020 | 28.06.2020
12 | Prepare documentation | Arnab |  | 4% | 3.296 | 10 | 25.06.2020 | 28.06.2020
13 | Milestone-related discussions | Everyone |  | 10% | 8.24 | - | 23.06.2020 | 29.06.2020

## Milestone8
Milestone 8: Final report
ID | Description | Assignee | Supporters | Effort (%) | Hours | Dependencies | Planned starting date | Planned end date | Remaining | 0%
1 | Create the final report document. | Lauro |  | 3% | 1.0815 | - | 18.05.2020 | 18.05.2020 | Total hours | 36.05
2 | Overview Section: Provide an overview of each milestone, the problems encountered, and the solutions for each of the problems. | Lauro |  | 7% | 2.5235 | M1 - M7 | Continuous, updated at the planned end date for each specific milestone task
3 | Conceptual Model Section: Explain the conceptual model by focusing on the assumptions made by the team. | Lauro | Chandan | 7% | 2.5235 | M3 | 19.05.2020 | 22.05.2020
4 | Data Analysis Section: Explain the results of the data analysis and the distributions used to model the system. | Lauro | Vinay | 10% | 3.605 | M4 | 26.05.2020 | 29.05.2020
5 | Model & Validation Section: Explain the model and its limitations, as well as the modifications made in order to make it more realistic. | Lauro | Anjan Kavya | 10% | 3.605 | M5, M6 | 16.06.2020 | 19.06.2020
6 | Recommendations Section: Explain the relevant experiments, their results and their feasibility. | Lauro | Arnab | 10% | 3.605 | M7 | 30.06.2020 | 03.07.2020
7 | Cost Overview Section: Provide an overview of the cost spent per milestone, as well as comments on how the planned costs were adjusted to deal with unforeseen challenges. | Lauro | Everyone | 5% | 1.8025 | M1 - M7 | Continuous, updated at the planned end date for each specific milestone task
8 | Team Section: Provide an overview of the team as a whole during the project, how we have worked together, whether there were any challenges. | Lauro |  | 10% | 3.605 | M1 - M7 | Continuous, updated at the planned end date for each specific milestone task
9 | Team Section: For each of the members, provide an overview of the project performance, as well as personal comments regarding the course. | Lauro |  | 10% | 3.605 | M1 - M7 | Continuous, updated at the planned end date for each specific milestone task
10 | Format the final report. | Lauro |  | 5% | 1.8025 | 1 - 9 | 30.06.2020 | 03.07.2020
11 | Read and review the final report. | Everyone |  | 15% | 5.4075 | 1 - 9 | 03.07.2020 | 04.07.2020
12 | Implement changes from the review of the final report. | Lauro |  | 8% | 2.884 |  | 04.07.2020 | 06.07.2020

## ProjectProgress
|  |  | Number of tasks |  | Percentage
| Week | Date Ends | Planned | Done | Planned | Done
| Start | 2020-04-21 | 0 | 0 | 0 | 0
Milestone1 | 1 | 2020-04-28 | 7 | 7 | 5.83 | 5.83 | 5.83%
Milestone2 | 2 | 2020-05-05 | 10 | 8 | 14.17 | 12.5 | 8.33%
Milestone3 | 3 | 2020-05-12 | 16 | 18 | 27.5 | 27.5 | 13.33%
Milestone 4 | 4 | 2020-05-19 | 10 | 10 | 35.83 | 35.83 | 8.33%
| 5 | 2020-05-26 | 10 | 8 | 44.17 | 42.5 | 8.33%
Milestone 5 | 6 | 2020-06-02 | 15 | 15 | 56.67 | 55 | 12.5%
Milestone 6 | 7 | 2020-06-09 | 9 | 11 | 64.17 | 64.17 | 7.5%
| 8 | 2020-06-16 | 13 | 13 | 75 | 75 | 10.83%
Milestone 7 | 9 | 2020-06-23 | 12 | 12 | 85 | 85 | 10%
| 10 | 2020-06-30 | 6 | 6 | 90 | 90 | 5%
Milestone 8 | 11 | 2020-07-07 | 12 | 0 | 100 |  | 10%
Formulas:
Date Ends = [Date Ends, row above]+7